## POA&M Open Items
Remediation Plan (POA&M)
POAM ID | Controls | Weakness Description | Risk Rating | Point of Contact | Resources Required | Remediation Plan | Scheduled Completion Date | Status | Status Date
POA&M-001 | IA-2 | Contractors and researchers lack unique credentials; shared accounts exist for temporary personnel. | Moderate | ISSO | Reallocation | Inventory all contractor accounts. Create unique credentials for each contractor and researcher. Disable all shared accounts. | 2026-07-15 | In Progress | 2026-06-25
POA&M-002 | AC-3 | Legacy service accounts lack MFA enforcement. | High | ISSO | Reallocation | Identify all legacy service accounts. Migrate accounts to IAM roles. Enforce MFA on all remaining accounts. | 2026-07-30 | In Progress | 2026-06-25
POA&M-003 | SC-7 | No intrusion detection at API Gateway boundary. | Medium | Security Team | Unfunded | Evaluate IDS/IPS options for API Gateway. Select and procure solution. Deploy and test. | 2026-08-30 | Planned | 2026-06-25
POA&M-004 | SI-4 | GuardDuty findings do not trigger automated alerts. | High | ISSO | Reallocation | Configure CloudWatch to monitor GuardDuty. Create SNS alert thresholds. Test alerting with simulated findings. | 2026-08-15 | In Progress | 2026-06-25
POA&M-005 | AU-2 | Audit logs not reviewed on a regular schedule. | Low | ISSO | Funded | Define weekly log review schedule. Assign reviewer rotation. Complete first review and document results. | 2026-07-01 | In Progress | 2026-06-25

## Key
Risk Rating Key
Risk Rating | Definition
High | Requires immediate action. Exploitation likely.
Medium | Requires planned action within 90 days.
Low | Address during normal maintenance cycle.
Status Key
Status | Definition
Planned | Remediation scheduled but not yet started
In Progress | Active work underway
Completed | Remediation verified and closed
Resources Key
Resources Required | Definition
Funded | Budget already allocated
Unfunded | Budget needs to be requested
Reallocation | Existing budget being redirected
Column Definitions
Column | Description
POAM ID | Unique identifier for tracking
Controls | NIST 800-53 control ID
Weakness Description | Specific deficiency or gap
Risk Rating | Prioritization level (High/Medium/Low)
Point of Contact | Person or role responsible
Resources Required | Funding status (Funded/Unfunded/Reallocation)
Remediation Plan | Specific steps to resolve the weakness
Scheduled Completion Date | Target date for remediation
Status | Current progress (Planned/In Progress/Completed)
Status Date | Date status was last updated