## Sheet1
Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Score | Risk Level | Treatment | Remediation Plan | Owner | Target Date
R-001 | Insufficient EC2 instances to run the LTS system globally, potentially leading to a critical outage or system degradation. | Technical | 4 | 3 | 12 | Medium | Mitigate | Implement ASGs across us-gov-west-1 and us-gov-east-1 with 70% CPU scaling trigger. | CloudOps | Q3 2026
R-002 | Improperly configured S3 bucket policies, allowing unauthorized users to access logs of other customers’ data. | Technical | 3 | 4 | 12 | Medium | Mitigate | Implement bucket policies on S3 buckets managing sensitive user data, restricting access to database management staff. Enforce Block Public Access at account level. | CloudOps | Q2 2026
R-003 | IAM resource-based policies improperly configured, not preventing systems from incorrectly being deployed in a non-GovCloud region. | Technical | 2 | 3 | 6 | Low | Mitigate | Write and deploy an IAM policy for the Developers group restricting EC2 deployments to GovCloud regions only. Apply inline policies to any other users with EC2 deployment access who are not in the Developers group. | CloudOps | Q2 2026
R-004 | Credentials of terminated employees and contractors are not being removed from the system, leaving inactive accounts which can be exploited. | Operational | 5 | 4 | 20 | High | Mitigate | Run an IAM credential report and remove stale or inactive credentials. Implement quarterly credential audits and include credential removal in the employee offboarding process. | IAM Team | Q2 2026
R-005 | No clear chain-of-command in the case of a data breach, leaving employees and contractors to divulge sensitive information to unauthorized personnel. | Operational | 5 | 3 | 15 | Medium | Mitigate | Document and implement an incident response plan with clear chain-of-command, roles, and escalation paths. Provide annual training to all employees and contractors. | ISSO | Q2 2026
R-006 | Customers' employees using LTS mobile app may lose or mishandle devices containing cached CUI data, exposing sensitive information outside the system boundary. | Operational | 5 | 3 | 15 | Medium | Transfer | Transfer to customer via Terms of Service. Document that device security, including remote wipe and monitoring, is customer responsibility. | Legal | N/A
R-007 | No documented SSP exists for LTS, leaving control implementations undefined. | Compliance | 5 | 3 | 15 | Medium | Mitigate | Draft and maintain a System Security Plan (SSP) mapped to NIST 800-171 controls. Update annually. | ISSO | Q2 2026
R-008 | Prime contractors do not clearly communicate to subcontractors which elements are designated as CUI, leaving subs uncertain about what requires protection. | Compliance | 4 | 4 | 16 | Medium | Accept | Prime contractors control CUI communication to subcontractors; LTS has no ability to enforce. Reassess annually or if contract terms change. | ISSO | N/A
R-009 | LTS deployed in standard AWS commercial regions (us-west-1) instead of AWS GovCloud, potentially violating CUI handling requirements and FedRAMP compliance. | Compliance | 5 | 3 | 15 | Medium | Mitigate | Inventory all resources currently deployed outside GovCloud. Migrate identified resources to us-gov-west-1. Update Infrastructure as Code (IaC) templates to enforce GovCloud as default. | CloudOps | Q3 2026
R-010 | A subcontractor handling CUI-related logistics data runs their operations on the clear web, using unencrypted drives and HTTP for traffic flows, exposing CUI to interception and unauthorized access. | Third-Party | 5 | 3 | 15 | Medium | Transfer | Replace vendor or contractually require FedRAMP Moderate compliance with audit rights. | Procurement | Q3 2026
R-011 | Subcontractor outsources work involving CUI to a fourth party without prime approval, creating unknown security gaps and potential contract violation. | Third-Party | 3 | 4 | 12 | Medium | Transfer | Add contract clause prohibiting unauthorized outsourcing. Require flow-down clauses to fourth parties. | Legal | Q2 2026
R-012 | Customers' employees using LTS mobile app may discuss CUI-related data in uncontrolled settings, potentially exposing sensitive information outside the authorized environment. | Third-Party | 5 | 2 | 10 | Medium | Transfer | Transfer to customer via Terms of Service. Include user training and data handling requirements. | Legal | N/A
Physical security controls inherited from AWS GovCloud. No LTS-owned physical assets.